## Cover page
Project Name : | Elasticsearch project
Customer Name : | CS
Create by : | XXXX
Document Rev : | 0.6.1

## Project plan - updated
Task | PIC | CIMB Team | Status | Progress (%) | Feb |  |  | March |  |  |  | April | [29 empty] | May | [30 empty] | June | [29 empty] | July | [30 empty] | Aug | [29 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | March
[5 empty] | w2 | w3 | w4 | w1 | w2 | w3 | w4 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 15 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Phase 0 : System desing. | CTC, CIMB |  | Done | 100% | bar: Feb w4 to March w4
Gathering Infor Design SIT, DEV,UAT,PROD Sign Off - Connection preparation | CTC, CIMB |  | Done | 100% | bar: Feb w4 to March w2
- Technical readiness brief - Elastic search technology | CTC, CIMB |  | Done | 100% | bar: March w1
- VPN preparation and confirmation | CTC, CIMB |  | Done | 100% | bar: March w2 to March w4
- Jump host access and collaboration confirm | CTC, CIMB |  | Done | 100% | bar: March w2 to March w4
- Technical readiness content preparation | CTC, CIMB |  | Done | 100% | bar: March w4 to April 3
- Technical readiness - training day | CTC, CIMB |  | Done | 100% | bar: March w4; April 4
Phase 1 Dev: Project implementation | CTC, CIMB, CRIF |  | Inprogress | 90% | bar: Feb w2 to April 5; April 9 to April 11; April 17 to April 19; April 22 to April 26; April 29 to May 3; May 7 to May 10; May 13 to May 17; May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Sep 2 to Sep 6; Sep 9 to Sep 13; Sep 16 to Sep 20; Sep 23 to Sep 27; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Nov 2; Nov 5 to Nov 9; Nov 12 to Nov 16; Nov 19 to Nov 23; Nov 26 to Nov 30; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 11; Jan 15 to Jan 19; Jan 22 to Jan 25; Jan 28 to Feb 1; Feb 4 to Feb 8; Feb 11 to Feb 15; Feb 18 to Feb 22; Feb 25 to March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
Information Gathering and confirm AWS Design and ELK Design. Finalise design for DEV | CTC, CIMB |  | Inprogress | 95% | bar: April 9 to April 10
: Submtted design version 0.1 | CTC |  | Done | 100% | bar: April 10
: Review & Feedback design version 0.1 | CIMB |  | Done | 100% | bar: April 11
: Submtted design version 0.2 | CTC |  | Done | 100% | bar: April 17
: Review & Feedback design version 0.2 | CIMB |  | Done | 100% | bar: April 18 to April 19
: Submtted design version 0.8 with Terraform script | CTC |  | Done | 100% | bar: April 18; April 22
: Review & Feedback design version 0.8 with Terraform script | CIMB |  | Done | 100% | bar: April 18; April 22
: Submtted design version 0.9.1 with Terraform script | CTC |  | Done | 100% | bar: April 19; April 22
: Review & Feedback design version 0.9.1 with Terraform script | CIMB |  | Done | 100% | bar: April 22
: Review & Feedback design version 1.0, Parameter sheet and Terraforom script. |  |  | Done | 100% | bar: April 22
Final review and confirm AWS Design and ELK Design for DEV - Sign Off documents. | CTC, CIMB |  | In progess | 80% | bar: April 17 to April 19; April 22 to April 26; April 29 to May 3; May 7 to May 10; May 13 to May 17; May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to July 31
Start Terraform and Ansible Setup and Testing (Need AWS access, VPN to Jumpbox and setup Jumpbox), Provision Dev,ELK | CTC, CIMB |  | Done | 100% | bar: April 17 to April 19; April 22 to April 26; April 29 to May 3; May 7 to May 10; May 13 to May 17; May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to July 31
Meeting - Integration meeting - CS Insigh and MS AD or Microsoft Entra ID. | CTC, CIMB |  | Done | 100% | bar: April 11; April 19
: Submit information request to CS (Azure Entra ID integration diagram and parameter sheet) | CTC, CIMB, CRIF |  | Done | 100% | bar: April 11; April 19
: Provide information from Elasticsearch | CTC, ES, CIMB |  | Done | 100% | bar: April 11; April 19
: Confirm information with CRIF | CTC, CIMB, CRIF |  | Done | 100% | bar: April 11; April 18
Elasticsearch License activation | CTC, CIMB, ES |  | Done | 100% | bar: April 11; April 17 to April 19; April 22 to April 24
: Contract process - License | CTC, ES |  | Done | 100% | bar: April 11; April 17
: Confirm activation - License | CTC, CIMB, ES |  | Done | 100% | bar: April 24
Prepare for Microsoft EntraID application integration | CIMB, CRIF |  | Done | 100% | bar: April 24
: Provide information and KB. | CRIF, CIMB |  | Done | 100% | bar: April 24 to April 25
: Prepare firewall between MS EntraID service to Elasticsearch DEV (Refer to design document) | CIMB |  | Done | 100% | bar: April 25; May 2 to May 3; May 7
: Prepare DNS record for Elasticsearch DEV (Refer to design document) | CIMB |  | Done | 100% | bar: April 25; May 7 to May 8
: Prepare SSL record for Elasticsearch DEV (Refer to design document) | CIMB |  | Done | 100% | bar: April 25; May 7 to May 10
Test - Integration Kibana and Elastic API with Azure EntraID (INRA ) | CTC, CIMB |  | Done | 100% | bar: April 25 to April 26; May 1 to May 3; May 13 to May 14
Integration Kibana and Elastic API with Azure EntraID (INRA ) | CTC, CIMB |  | Done | 100% | bar: April 29 to May 3
System Integration configuration: | CTC, CIMB, CRIF |  | In progess | 90% | bar: April 29 to May 3; May 14 to May 17; May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26
Integration clarification & Meeting. | CTC, CIMB, CRIF |  | Done | 100% | bar: May 14 to May 17; May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21
: Meeting and clarification about S1 and Elasticsearch integration - user role and Firewall port. | CTC, CIMB, CRIF |  | Done | 100% | bar: May 14 to May 17; May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21
: Meeting and clarification about Filebeat and Elasticsearch integration - credentail and SSL. | CTC, CIMB, CRIF |  | Done | 100% | bar: May 14 to May 17; May 20 to May 24; May 27 to May 31; June 3 to June 7
: Meeting and clarification about system integration by using LDAP user. | CTC, CIMB, CRIF |  | Done | 100% | bar: May 14 to May 17; May 20 to May 24; May 27 to May 31; June 3 to June 7
: Meeting and clarification about system integration with LDAP. | CTC, CIMB, CRIF |  | Done | 100% | bar: May 14 to May 17; May 20 to May 24; May 27 to May 31; June 3 to June 4
: Meeting and clarification about system integration with IntraID | CTC, CIMB, CRIF |  | Done | 100% | bar: May 14 to May 17; May 20 to May 24; May 27 to May 31; July 24
Integration prepation and implementation. | CTC, CIMB, CRIF |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26
Prepare for new SSL - Logstash | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28
: Provide CSR information and KB for change request | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28
: Process issue certificate on CIMB CA server. | CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 26 to June 27
: Test and confirm integration new SSL. | CTC |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 28
: Associated new SSL with Logstash service. | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; July 8 to July 9
: Test and confirm configuration. | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; July 8 to July 9
Prepare for new SSL - Filebeat | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 26 to June 28; July 1 to July 5; July 8 to July 12
: Provide CSR information and KB for change request | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 26 to June 27; July 8 to July 11
: Process issue certificate on CIMB CA server. | CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 28; July 1; July 12
: Test and confirm integration new SSL. | CTC |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; July 4 to July 5; July 12
: Associated new SSL with Logstash service. | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; July 8 to July 9; July 12
: Test and confirm configuration. | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; July 8 to July 9; July 12
Prepare for new LDAP user (Total 3 users) | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; July 9 to July 12
: Provide user information and KB for change request | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 26 to June 27; July 9 to July 10; July 12
: Create user on LDAP with test login | CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; July 1 to July 5; July 11 to July 12
: Test and confirm new user work properly | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; July 1 to July 5
Prepare for PROD MS EntraID - Enterprise App | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; July 9 to July 12; July 16 to July 17
: Provide information and KB for change request | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 26 to June 27; July 9 to July 11; July 16 to July 19; July 23 to July 26; July 30
: Configure MS EntraID integration with Elasticsearch | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; July 9 to July 11; July 16 to July 17; July 24 to July 25; Aug 5 to Aug 6
: Test and confirm integration had done. | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; July 9 to July 11; July 16 to July 17; July 24 to July 25; Aug 5 to Aug 6
Prepare for NOVA AD - System integration | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; July 11 to July 12; July 18 to July 19
: Provide information and KB for change request | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 26 to June 27; July 11 to July 12; July 18 to July 19
: Prepare user on NOVA - LDAP (cimbthai.com) | CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; July 11 to July 12; July 18 to July 19
: Configure EKS and Elasticsearch integration with NOVA LDAP. | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; July 11 to July 12; July 18 to July 19
: Test and confirm integration had done. | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; July 11 to July 12; July 18 to July 19
Prepare for CS S1 - System integration | CTC, CIMB, CRIF |  | In progess | 0% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to Aug 2; Aug 5 to Aug 9; Sep 9 to Sep 11
Test - Integration - CS Insight | CTC, CRIF |  | In progess | 0% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to Aug 2; Aug 5 to Aug 9; Sep 9 to Sep 11
Integration - CS Insight | CTC, CRIF |  | In progess | 0% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to Aug 2; Aug 5 to Aug 9; Sep 9 to Sep 11
DEV - System upgrade from 10.11.x to 10.13.4 | CTC, CIMB, CRIF |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to July 31; Sep 2
EKS - Upgrade, Verify and Test | CTC, CRIF |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to July 31; Sep 2
Filebeat - Upgrade, Verify and Test | CTC, CRIF |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to July 31; Sep 2
Phase 2 SIT: Project implementation |  |  | Inprogress | 70% | bar: Feb w2 to April 5; April 9 to April 11; April 17 to April 19; April 22 to April 26; April 29 to May 3; May 7 to May 10; May 13 to May 17; May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Sep 2 to Sep 6; Sep 9 to Sep 13; Sep 16 to Sep 20; Sep 23 to Sep 27; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Nov 2; Nov 5 to Nov 9; Nov 12 to Nov 16; Nov 19 to Nov 23; Nov 26 to Nov 30; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 11; Jan 15 to Jan 19; Jan 22 to Jan 25; Jan 28 to Feb 1; Feb 4 to Feb 8; Feb 11 to Feb 15; Feb 18 to Feb 22; Feb 25 to March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
Information Gathering and confirm AWS Design and ELK Design. Finalise design for SIT | CTC, CIMB |  | In progress | 80% | bar: April 9 to April 10
: Submtted design version 0.1 | CTC |  | Done | 100% | bar: April 10
: Review & Feedback design version 0.1 | CIMB |  | Done | 100% | bar: April 11
: Submtted design version 0.2 | CTC |  | Done | 100% | bar: April 17
: Review & Feedback design version 0.2 | CIMB |  | Done | 100% | bar: April 18 to April 19
: Submtted design version 0.3 | CTC |  | Done | 100% | bar: April 18; April 22
: Review & Feedback design version 0.3 | CIMB |  | Done | 100% | bar: April 18; April 22
: Review & Feedback design version 0.9.1 with Terraform script | CIMB |  | Done | 100% | bar: April 22
: Review & Feedback design version 1.0, Parameter sheet and Terraforom script. |  |  | In progess | 80% | bar: April 22; Aug 14
Final review and confirm AWS Design and ELK Design for SIT - Sign Off documents. | CTC, CIMB |  | In progess | 80% | bar: April 17 to April 19; April 22 to April 24
Start Terraform and Ansible Setup and Testing (Need AWS access, VPN to Jumpbox and setup Jumpbox), Provision SIT,ELK | CTC, CIMB |  | Done | 100% | bar: April 17 to April 19; April 22 to April 26; April 29; Aug 16
Meeting - Integration meeting - CRIF Insigh and MS AD or Microsoft Entra ID. | CTC, CIMB |  | Done | 100% | bar: April 11; April 19
Submit information request to CS Internal Change (Change request) | CTC, CIMB, CRIF |  | Done | 100% | bar: April 11; April 19
: Provide information in CR form (Excel) for Security group between ESK and Elasticsearch server. | CTC, ES, CIMB |  | Done | 100% | bar: April 11; April 19; Aug 14
: Provide information in CR form (Excel) for DNS Record of SIT environment. | CTC, CIMB, CRIF |  | Done | 100% | bar: April 11; April 18; Aug 14
: Provide information in CR form (Excel) for SSL certificate of SIT environment. | CTC, CIMB, ES |  | Done | 100% | bar: April 11; April 17 to April 19; April 22 to April 24; Aug 14
: Provide information in CR form (Excel) for user and group on Non-PROD AD of SIT environment. | CTC, ES |  | Done | 100% | bar: April 11; April 17; Aug 14
: Provide information in CR form (Excel) for user and group on PROD Azure Entra ID of SIT environment. | CTC, CIMB, ES |  | Done | 100% | bar: April 24; Aug 14
Process change for request for each items. | CIMB, CRIF |  | Done | 100% | bar: April 24
: Security Group (FW) port allow and verification | CRIF, CIMB |  | Done | 100% | bar: April 24 to April 25
CRIF Insight - Elastic search API : 9200 |  |  | Done | 100% | bar: April 24 to April 25; Aug 16; Aug 21
CRIF Insight – Logstash : 9600 |  |  | Done | 100% | bar: April 24 to April 25; Aug 16; Aug 21
Admin user – kibana : 5601 |  | 5434:20 | Done | 100% | bar: April 24 to April 25; Aug 16; Aug 21
Filebeat – Logstash : 5044 |  | 4877:20 | Done | 100% | bar: April 24 to April 25; Aug 16; Aug 21
LDAPs (EKS – ES server) : 636 |  |  | Done | 100% | bar: April 24 to April 25; Aug 16; Aug 21
All user to Entra ID : 443 |  |  | Done | 100% | bar: April 24 to April 25; Aug 16; Aug 21
: DNS Record create and verification | CIMB |  | Done | 100% | bar: April 25; May 2 to May 3; May 7
Name record : crde-kibana-sit.cimbthai.com |  |  | Done | 100% | bar: April 25; May 2 to May 3; May 7; Aug 16; Aug 21
Name record : crde-api-sit.cimbthai.com |  |  | Done | 100% | bar: April 25; May 2 to May 3; May 7; Aug 16; Aug 21
Name record : crde-log-sit.cimbthai.com |  |  | Done | 100% | bar: April 25; May 2 to May 3; May 7; Aug 16; Aug 21
Name record : crde-filebeat-sit.cimbthai.com |  |  | Done | 100% | bar: April 25; May 2 to May 3; May 7; Aug 16; Aug 21
: SSL and verification | CIMB |  | Done | 100% | bar: April 25; May 7 to May 8
Prepare for new SSL - Logstash: (SAN : crde-log-sit.cimbthai.com) |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
: Provide CSR information and KB for change request |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
: Process issue certificate on CIMB CA server. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
: Test and confirm integration new SSL. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
: Associated new SSL with Logstash service. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
: Test and confirm configuration. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
Prepare for new SSL - kibana: (SAN : crde-kibana-sit.cimbthai.com) |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
: Provide CSR information and KB for change request |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
: Process issue certificate on CIMB CA server. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
: Test and confirm integration new SSL. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
: Associated new SSL with kibana service. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
: Test and confirm configuration. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
Prepare for new SSL - API: (SAN : ccrde-api-sit.cimbthai.com) |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
: Provide CSR information and KB for change request |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
: Process issue certificate on CIMB CA server. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
: Test and confirm integration new SSL. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
: Associated new SSL with API service. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
: Test and confirm configuration. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
Prepare for new SSL - Filebeat: (SAN : crde-filebeat-dev.cimbthai.com) |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
: Provide CSR information and KB for change request |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
: Process issue certificate on CIMB CA server. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
: Test and confirm integration new SSL. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
: Associated new SSL with Filebeat service. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
: Test and confirm configuration. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 21 to Aug 22
: Non-PROD user and group create and verification | CIMB |  | Done | 100% | bar: April 25; May 7 to May 10
: Number-1 : The account between Elasticsearch server and EKS Server : sit-es2eks@nova.sit.cimbthai |  |  | Done | 100% | bar: April 25; May 7 to May 10; Aug 19
: Number-2 : The account between Elasticsearch and CRIF Insight connection API : sit-es2insight@nova.sit.cimbthai |  |  | Done | 100% | bar: April 25; May 7 to May 10; Aug 19
: Number-3 : The account between CRIF Insight and Logstash to perform health check and to get pipeline statistics : sit-insight2log@nova.dev.cimbthai |  |  | Done | 100% | bar: April 25; May 7 to May 10; Aug 19
: PROD Entra ID user and group create and verification |  |  | In progess | 0% | bar: April 25; May 7 to May 10
Prepare for configuration of enterprise application on Azure Entra ID Application name : CSS-kibana-sit |  |  | In progess | 0% | bar: April 25; May 7 to May 10; Aug 19; Sep 5 to Sep 6
Prepare for configuration of enterprise application on Azure Entra ID Redirect URIs : https://prod.com:5601/api/security/oidc/callback |  |  | In progess | 0% | bar: April 25; May 7 to May 10; Aug 19; Sep 5 to Sep 6
Prepare for configuration of enterprise application on Azure Entra ID Logout URIs : https://cs-sit.xx.com:5601/security/logged_out |  |  | In progess | 0% | bar: April 25; May 7 to May 10; Aug 19; Sep 5 to Sep 6
Prepare for configuration of enterprise application on Azure Entra ID Tokeng group: sAMAccount Name |  |  | In progess | 0% | bar: April 25; May 7 to May 10; Aug 19; Sep 5 to Sep 6
Prepare for configuration of enterprise application on Azure Entra ID API Permision : Group member ALL, Read and User Read. |  |  | In progess | 0% | bar: April 25; May 7 to May 10; Aug 19; Sep 5 to Sep 6
Deployment Elasticsearch Server | CTC, CIMB, CRIF |  | Done | 100% | bar: April 11; April 19
: Prepare VPC resource for AWS system | CTC, ES, CIMB |  | Done | 100% | bar: April 11; April 19; Aug 21
: Provide deployment script and other deploymen source for Elasticsearch on SIT. (On/To the Jumphost) | CTC, CIMB, CRIF |  | Done | 100% | bar: April 11; April 18; Aug 21
: Review the script with detail of deployment and parameter of each module include perform test before confirm starting. |  |  | Done | 100% | bar: April 11; April 18; Aug 21
: Perform deploy by ELK script to deploy Kibana, logstash and API module. (Deploy and configure as 1 script) | CTC, CIMB, ES |  | Done | 100% | bar: April 11; April 17 to April 19; April 22 to April 24; Aug 21
: Perform basic verification. |  |  | Done | 100% | bar: April 11; April 17; Aug 21
: Confirm basic deployment as desing and parameter sheet. |  |  | Done | 100% | bar: April 11; April 17; Aug 21
Deployment Filebeat | CTC, CIMB, CRIF |  | Done | 100% | bar: April 11; April 19; Aug 21 to Aug 22; Sep 2
: Prepare resource for Filebeat on EKS system. | CTC, ES, CIMB |  | Done | 100% | bar: April 11; April 19; Aug 21 to Aug 22; Sep 2
: Provide deployment yml script to CIMB | CTC, CIMB, CRIF |  | Done | 100% | bar: April 11; April 18; Aug 21 to Aug 22; Sep 2
: Perform deploy with ynl and SSL. |  |  | Done | 100% | bar: April 11; April 18; Aug 21 to Aug 22; Sep 2
: Perform verification - Connection and sample log file. | CTC, CIMB, ES |  | Done | 100% | bar: April 11; April 17 to April 19; April 22 to April 24; Aug 21 to Aug 22; Sep 2
: Confirm basic deployment as desing and parameter sheet. | CTC, ES |  | Done | 100% | bar: April 11; April 17; Aug 21 to Aug 22; Sep 2
System Integration configuration: | CTC, CIMB, CRIF |  | In progess | 30% | bar: April 29 to May 3; May 14 to May 17; May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; Aug 22 to Aug 23
Integration prepation and implementation. | CTC, CIMB, CRIF |  | In progess | 30% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; Aug 22 to Aug 23
Perform configure Elasticsearch | CTC, CIMB |  | In progess | 0% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; Aug 22 to Aug 23
: Perform review and integration by checking communication between LogStash2Insight | CTC, CIMB |  | In progess | 0% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 26 to June 27; Aug 22 to Aug 23; Sep 9 to Sep 11; Sep 16 to Sep 20
: Perform review and integration by checking communication between API2Insight | CIMB |  | In progess | 0% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; July 1 to July 5; Aug 22 to Aug 23; Sep 9 to Sep 11; Sep 16 to Sep 20
: Perform review and integration by checking communication between LogStash2Filebeat | CTC, CIMB |  | In progess | 0% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; July 1 to July 5; Aug 22 to Aug 23; Sep 9 to Sep 11; Sep 16 to Sep 20
Prepare for NOVA AD - System integration | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; Aug 22 to Aug 23
: Provide information and KB for change request | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 26 to June 27; Aug 22 to Aug 23
: Prepare user on NOVA - LDAP (cimbthai.com) | CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; Aug 22 to Aug 23
: Configure EKS and Elasticsearch integration with NOVA LDAP. | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; Aug 22 to Aug 23
: Test and confirm integration had done. | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; Aug 22 to Aug 23
Prepare for PROD MS EntraID - Enterprise App | CTC, CIMB |  | In progess | 40% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; Aug 22 to Aug 23
: Provide information and KB for change request | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 26 to June 27; Aug 22 to Aug 23
: Configure MS EntraID integration with Elasticsearch | CTC, CIMB |  | In progess | 0% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; Aug 22 to Aug 23; Sep 5 to Sep 6
: Test and confirm integration had done. | CTC, CIMB |  | In progess | 0% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; Aug 22 to Aug 23; Sep 5 to Sep 6
Prepare for CRIF S1 - System integration | CTC, CIMB, CRIF |  | In progess | 0% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; Sep 16 to Sep 20
Test - Integration - CRIF Insight | CTC, CRIF |  | In progess | 0% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; Sep 16 to Sep 20
Integration - CRIF Insight | CTC, CRIF |  | In progess | 0% | bar: Sep 16 to Sep 20
Phase 3 UAT: Project implementation |  |  | Inprogress | 70% | bar: Feb w2 to April 5; April 9 to April 11; April 17 to April 19; April 22 to April 26; April 29 to May 3; May 7 to May 10; May 13 to May 17; May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Sep 2 to Sep 6; Sep 9 to Sep 13; Sep 16 to Sep 20; Sep 23 to Sep 27; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Nov 2; Nov 5 to Nov 9; Nov 12 to Nov 16; Nov 19 to Nov 23; Nov 26 to Nov 30; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 11; Jan 15 to Jan 19; Jan 22 to Jan 25; Jan 28 to Feb 1; Feb 4 to Feb 8; Feb 11 to Feb 15; Feb 18 to Feb 22; Feb 25 to March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
Information Gathering and confirm AWS Design and ELK Design. Finalise design for uat | CTC, CIMB |  | In progress | 30% | bar: April 9 to April 10
: Submtted design version 0.1 | CTC |  | Done | 100% | bar: April 10; Aug 19
: Review & Feedback design version 0.1 | CIMB |  | In progess | 0% | bar: April 11; Aug 20
: Submtted design version 0.2 | CTC |  | In progess | 0% | bar: April 17; Aug 21
: Review & Feedback design version 0.2 | CIMB |  | In progess | 0% | bar: April 18 to April 19; Aug 22
: Submtted design version 0.3 | CTC |  | In progess | 0% | bar: April 18; April 22
: Review & Feedback design version 0.3 | CIMB |  | In progess | 0% | bar: April 18; April 22
: Review & Feedback design version 0.9.1 with Terraform script | CIMB |  | In progess | 0% | bar: April 22
: Review & Feedback design version 1.0, Parameter sheet and Terraforom script. |  |  | In progess | 0% | bar: April 22; Aug 23
Final review and confirm AWS Design and ELK Design for uat - Sign Off documents. | CTC, CIMB |  | In progess | 0% | bar: April 17 to April 19; April 22 to April 24; Aug 23
Start Terraform and Ansible Setup and Testing (Need AWS access, VPN to Jumpbox and setup Jumpbox), Provision uat,ELK | CTC, CIMB |  | In progess | 0% | bar: April 17 to April 19; April 22 to April 26; April 29
Meeting - Integration meeting - CS Insigh and MS AD or Microsoft Entra ID. | CTC, CIMB |  | In progess | 0% | bar: April 11; April 19
Submit information request to CS Internal Change (Change request) | CTC, CIMB, CRIF |  | Done | 100% | bar: April 11; April 19; Aug 13
: Provide information in CR form (Excel) for Security group between ESK and Elasticsearch server. | CTC, ES, CIMB |  | Done | 100% | bar: April 11; April 19; Aug 13
: Provide information in CR form (Excel) for DNS Record of uat environment. | CTC, CIMB, CRIF |  | Done | 100% | bar: April 11; April 18; Aug 13
: Provide information in CR form (Excel) for SSL certificate of uat environment. | CTC, CIMB, ES |  | Done | 100% | bar: April 11; April 17 to April 19; April 22 to April 24; Aug 13
: Provide information in CR form (Excel) for user and group on Non-PROD AD of uat environment. | CTC, ES |  | Done | 100% | bar: April 11; April 17; Aug 13
: Provide information in CR form (Excel) for user and group on PROD Azure Entra ID of uat environment. | CTC, CIMB, ES |  | Done | 100% | bar: April 24; Aug 13
Process change for request for each items. | CIMB, CRIF |  | Done | 100% | bar: April 24; Aug 13
: Security Group (FW) port allow and verification | CRIF, CIMB |  | Done | 100% | bar: April 24 to April 25; Aug 27 to Aug 28
CRIF Insight - Elastic search API : 9200 |  |  | Done | 100% | bar: April 24 to April 25; Aug 27 to Aug 28
CRIF Insight – Logstash : 9600 |  |  | Done | 100% | bar: April 24 to April 25; Aug 27 to Aug 28
Admin user – kibana : 5601 |  | 5434:20 | Done | 100% | bar: April 24 to April 25; Aug 27 to Aug 28
Filebeat – Logstash : 5044 |  | 4877:20 | Done | 100% | bar: April 24 to April 25; Aug 27 to Aug 28
LDAPs (EKS – ES server) : 636 |  |  | Done | 100% | bar: April 24 to April 25; Aug 27 to Aug 28
All user to Entra ID : 443 |  |  | Done | 100% | bar: April 24 to April 25; Aug 27 to Aug 28
: DNS Record create and verification | CIMB |  | Done | 100% | bar: April 25; May 2 to May 3; May 7; Aug 28 to Aug 29
Name record : crde-kibana-uat.cimbthai.com |  |  | Done | 100% | bar: April 25; May 2 to May 3; May 7; Aug 28 to Aug 29
Name record : crde-api-uat.cimbthai.com |  |  | Done | 100% | bar: April 25; May 2 to May 3; May 7; Aug 28 to Aug 29
Name record : crde-log-uat.cimbthai.com |  |  | Done | 100% | bar: April 25; May 2 to May 3; May 7; Aug 28 to Aug 29
Name record : crde-filebeat-uat.cimbthai.com |  |  | Done | 100% | bar: April 25; May 2 to May 3; May 7; Aug 28 to Aug 29
: SSL and verification | CIMB |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
Prepare for new SSL - Logstash: (SAN : crde-log-uat.cimbthai.com) |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
: Provide CSR information and KB for change request |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
: Process issue certificate on CIMB CA server. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
: Test and confirm integration new SSL. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
: Associated new SSL with Logstash service. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
: Test and confirm configuration. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
Prepare for new SSL - kibana: (SAN : crde-kibana-uat.cimbthai.com) |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
: Provide CSR information and KB for change request |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
: Process issue certificate on CIMB CA server. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
: Test and confirm integration new SSL. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
: Associated new SSL with kibana service. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
: Test and confirm configuration. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
Prepare for new SSL - API: (SAN : ccrde-api-uat.cimbthai.com) |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
: Provide CSR information and KB for change request |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
: Process issue certificate on CIMB CA server. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
: Test and confirm integration new SSL. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
: Associated new SSL with API service. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
: Test and confirm configuration. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
Prepare for new SSL - Filebeat: (SAN : crde-filebeat-dev.cimbthai.com) |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
: Provide CSR information and KB for change request |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
: Process issue certificate on CIMB CA server. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
: Test and confirm integration new SSL. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
: Associated new SSL with Filebeat service. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
: Test and confirm configuration. |  |  | Done | 100% | bar: April 25; May 7 to May 8; Aug 28 to Aug 29
: Non-PROD user and group create and verification | CIMB |  | Done | 100% | bar: April 25; May 7 to May 10
: Number-1 : The account between Elasticsearch server and EKS Server : uat-es2eks@nova.uat.cimbthai |  |  | Done | 100% | bar: April 25; May 7 to May 10; Aug 16
: Number-2 : The account between Elasticsearch and CRIF Insight connection API : uat-es2insight@nova.uat.cimbthai |  |  | Done | 100% | bar: April 25; May 7 to May 10; Aug 16
: Number-3 : The account between CRIF Insight and Logstash to perform health check and to get pipeline statistics : uat-insight2log@nova.dev.cimbthai |  |  | Done | 100% | bar: April 25; May 7 to May 10; Aug 16
: PROD Entra ID user and group create and verification |  |  | In progess | 0% | bar: April 25; May 7 to May 10; Sep 5 to Sep 6
Prepare for configuration of enterprise application on Azure Entra ID Application name : crde-kibana-uat |  |  | In progess | 0% | bar: April 25; May 7 to May 10; Aug 19; Sep 5 to Sep 6
Prepare for configuration of enterprise application on Azure Entra ID Redirect URIs : https://prod.com:5601/api/security/oidc/callback |  |  | In progess | 0% | bar: April 25; May 7 to May 10; Aug 19; Sep 5 to Sep 6
Prepare for configuration of enterprise application on Azure Entra ID Logout URIs : https://cdd-kibana-uat.xx.com:5601/security/logged_out |  |  | In progess | 0% | bar: April 25; May 7 to May 10; Aug 19; Sep 5 to Sep 6
Prepare for configuration of enterprise application on Azure Entra ID Tokeng group: sAMAccount Name |  |  | In progess | 0% | bar: April 25; May 7 to May 10; Sep 5 to Sep 6
Prepare for configuration of enterprise application on Azure Entra ID API Permision : Group member ALL, Read and User Read. |  |  | In progess | 0% | bar: April 25; May 7 to May 10; Sep 5 to Sep 6
Deployment Elasticsearch Server | CTC, CIMB, CRIF |  | Done | 100% | bar: April 11; April 19
: Prepare VPC resource for AWS system | CTC, ES, CIMB |  | Done | 100% | bar: April 11; April 19; Aug 22 to Aug 23; Aug 27
: Provide deployment script and other deploymen source for Elasticsearch on uat. (On/To the Jumphost) | CTC, CIMB, CRIF |  | Done | 100% | bar: April 11; April 18; Aug 22 to Aug 23; Aug 27
: Review the script with detail of deployment and parameter of each module include perform test before confirm starting. |  |  | Done | 100% | bar: April 11; April 18; Aug 22 to Aug 23; Aug 27
: Perform deploy by ELK script to deploy Kibana, logstash and API module. (Deploy and configure as 1 script) | CTC, CIMB, ES |  | Done | 100% | bar: April 11; April 17 to April 19; April 22 to April 24; Aug 22 to Aug 23; Aug 27
: Perform basic verification. |  |  | Done | 100% | bar: April 11; April 17; Aug 22 to Aug 23; Aug 27
: Confirm basic deployment as desing and parameter sheet. |  |  | Done | 100% | bar: April 11; April 17; Aug 22 to Aug 23; Aug 27
Deployment Filebeat | CTC, CIMB, CRIF |  | Done | 100% | bar: April 11; April 19; Aug 28; Sep 2
: Prepare resource for Filebeat on EKS system. | CTC, ES, CIMB |  | Done | 100% | bar: April 11; April 19; Aug 28; Sep 2
: Provide deployment yml script to CIMB | CTC, CIMB, CRIF |  | Done | 100% | bar: April 11; April 18; Aug 28; Sep 2
: Perform deploy with ynl and SSL. |  |  | Done | 100% | bar: April 11; April 18; Aug 28; Sep 2
: Perform verification - Connection and sample log file. | CTC, CIMB, ES |  | Done | 100% | bar: April 11; April 17 to April 19; April 22 to April 24; Aug 28; Sep 2
: Confirm basic deployment as desing and parameter sheet. | CTC, ES |  | Done | 100% | bar: April 11; April 17; Aug 28; Sep 2
System Integration configuration: | CTC, CIMB, CRIF |  | In progess | 30% | bar: April 29 to May 3; May 14 to May 17; May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; Aug 29 to Aug 30
Integration prepation and implementation. | CTC, CIMB, CRIF |  | In progess | 30% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; Aug 29 to Aug 30
Perform configure Elasticsearch | CTC, CIMB |  | In progess | 0% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; Aug 29 to Aug 30; Sep 9 to Sep 11; Sep 23 to Sep 27
: Perform review and integration by checking communication between LogStash2Insight | CTC, CIMB |  | In progess | 0% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 26 to June 27; Aug 29 to Aug 30; Sep 9 to Sep 11; Sep 23 to Sep 27
: Perform review and integration by checking communication between API2Insight | CIMB |  | In progess | 0% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; July 1 to July 5; Aug 29 to Aug 30; Sep 9 to Sep 11; Sep 23 to Sep 27
: Perform review and integration by checking communication between LogStash2Filebeat | CTC, CIMB |  | In progess | 0% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; July 1 to July 5; Aug 29 to Aug 30; Sep 9 to Sep 11; Sep 23 to Sep 27
Prepare for NOVA AD - System integration | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; Aug 29 to Aug 30
: Provide information and KB for change request | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 26 to June 27; Aug 29 to Aug 30
: Prepare user on NOVA - LDAP (cimbthai.com) | CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; Aug 29 to Aug 30
: Configure EKS and Elasticsearch integration with NOVA LDAP. | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; Aug 29 to Aug 30
: Test and confirm integration had done. | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; Aug 29 to Aug 30
Prepare for PROD MS EntraID - Enterprise App | CTC, CIMB |  | In progess | 40% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; Aug 29 to Aug 30
: Provide information and KB for change request | CTC, CIMB |  | Done | 100% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 26 to June 27; Aug 29 to Aug 30
: Configure MS EntraID integration with Elasticsearch | CTC, CIMB |  | In progess | 0% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; Aug 29 to Aug 30; Sep 5 to Sep 6
: Test and confirm integration had done. | CTC, CIMB |  | In progess | 0% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; Aug 29 to Aug 30; Sep 5 to Sep 6
Prepare for CS S1 - System integration | CTC, CIMB, CRIF |  | In progess | 0% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; Sep 23 to Sep 27
Test - Integration - CS Insight | CTC, CRIF |  | In progess | 0% | bar: May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; Sep 23 to Sep 27
Integration - CS Insight | CTC, CRIF |  | In progess | 0% | bar: Sep 23 to Sep 27
Phase 4 PROD: Project implementation | bar: Feb w2 to April 5; April 9 to April 11; April 17 to April 19; April 22 to April 26; April 29 to May 3; May 7 to May 10; May 13 to May 17; May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Sep 2 to Sep 6; Sep 9 to Sep 13; Sep 16 to Sep 20; Sep 23 to Sep 27; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Nov 2; Nov 5 to Nov 9; Nov 12 to Nov 16; Nov 19 to Nov 23; Nov 26 to Nov 30; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Feb 2; Feb 4 to Feb 9; Feb 11 to Feb 16; Feb 18 to Feb 22; Feb 25 to March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
Information Gathering and confirm AWS Design and ELK Design. Finalise design for PROD | CTC, CIMB | bar: Sep 2 to Sep 6; Sep 9 to Sep 13; Sep 16 to Sep 20; Jan 15; Jan 28; Feb 1 to Feb 2; Feb 4 to Feb 9; Feb 11 to Feb 16; Feb 18 to Feb 22; Feb 25 to Feb 28
Final review and confirm AWS Design and ELK Design for PROD - Sign Off documents. | CTC, CIMB | bar: Sep 16 to Sep 20; Sep 23 to Sep 27; Oct 30 to Oct 4; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
AWS IaC coding and development , Deploy AWS EC2 & ELK for PROD | CTC |  | Not start | Not start | bar: Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Nov 2; Nov 5 to Nov 9; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
Integration - CRIF Insight , Azure EntraID (INRA ) - Microsoft AD | CTC, CRIF |  | Not start | Not start | bar: Nov 5 to Nov 9; Nov 12 to Nov 16; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
| CTC |  | Not start | Not start | bar: Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
Kubernetes , CI/ CD | Opsta |  | Not start | Not start | bar: Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
APM (After Imp CRIF Insight) | CIMB |  | Not start | Not start | bar: Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
Prisma cloud | CIMB |  | Not start | Not start | bar: Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
Authen & Firewall | CIMB |  | Not start | Not start | bar: Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
Review and Sign Off 7 Docs (Discuss only one or separate ??? ) | CTC, Opsta,CRIF, CIMB |  | Not start | Not start | bar: Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
Application Implementation | bar: Feb w2 to April 5; April 9 to April 11; April 17 to April 19; April 22 to April 26; April 29 to May 3; May 7 to May 10; May 13 to May 17; May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Sep 2 to Sep 6; Sep 9 to Sep 13; Sep 16 to Sep 20; Sep 23 to Sep 27; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Nov 2; Nov 5 to Nov 9; Nov 12 to Nov 16; Nov 19 to Nov 23; Nov 26 to Nov 30; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Feb 2; Feb 4 to Feb 9; Feb 11 to Feb 16; Feb 18 to Feb 22; Feb 25 to March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
Soft Freeze | bar: April 29 to May 3; May 7 to May 10; May 13 to May 17; May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Sep 2 to Sep 6; Sep 9 to Sep 13; Sep 16 to Sep 20; Sep 23 to Sep 27; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Nov 2; Nov 5 to Nov 9; Nov 12 to Nov 16; Nov 19 to Nov 23; Nov 26 to Nov 30; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Feb 2; Feb 4 to Feb 9; Feb 11 to Feb 16; Feb 18 to Feb 22; Feb 25 to March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
Hard Freeze | bar: Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
Analysis | bar: April 29 to May 3; May 7 to May 10; May 13 to May 17; May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Oct 31; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Jan 31; Feb 4; Feb 11; Feb 18; March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
- Preliminary Analysis + As-is Credit Process Review (Mortgage , PL) | BA,CIMB | Risk , IT App | bar: April 29 to May 3; May 7 to May 10; May 13 to May 17; May 20 to May 24; May 27 to May 31; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
- Detailed Analysis - To-be Credit Process - Mortgage | BA | Risk , IT App | bar: May 1 to May 3; May 7 to May 10; May 13 to May 17; May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
- Detailed Analysis - To-be Credit Process - PL | BA | Risk , IT App | bar: June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to July 31; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
- Insight functionality review for CIMB | BU | Risk , IT App | bar: April 29 to May 3; May 7 to May 10; May 13 to May 17; May 20 to May 24; May 27 to May 31; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
- Insight functionality confirmation | BA | Risk , IT App | bar: May 1 to May 3; May 7 to May 10; May 13 to May 17; May 20 to May 24; May 27 to May 31; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
- Preliminary Analysis + technical architecture | CIMB,GT | IT App , Thiti, Be | Not start | Not start | bar: April 29 to May 3; May 7 to May 10; May 13 to May 17; May 20 to May 24; May 27 to May 31; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
- Detailed Analysis - To-be Architecture | CRIF | IT App , Thiti, Be | bar: June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
Documentation | bar: Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
FSD Prep - Mortage | CRIF | Risk , IT App | bar: June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
FSD - Mortgage - sign off | CIMB | Risk , IT App | bar: Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
FSD Prep - PL | CRIF | Risk , IT App | bar: July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to July 31; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
FSD - PL sign off | CRIF | Risk , IT App | bar: Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
FSD Prep - Insight + Non Functional | bar: Aug 1 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Oct 31; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Jan 31; Feb 4; Feb 11; Feb 18; March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
FSD - Insight + Non Functional sign off | bar: Aug 1 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Oct 31; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Jan 31; Feb 4; Feb 11; Feb 18; March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
TSD Prep (Crete and Review ???) | CRIF | IT App | bar: July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to July 31; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
TSD - sign off | CRIF | IT App | bar: July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to July 31; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
Technical | bar: April 29 to May 3; May 7 to May 10; May 13 to May 17; May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
System setup complete based on system requirement (Need support from CRIF from early stage ) | CIMB |  | Not start | Not start | bar: April 29 to May 3; May 7 to May 10; May 13 to May 17; May 20 to May 24; May 27 to May 31; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
AWS infrastructure is ready based on checklist provided by CRIF | CIMB |  | Not start | Not start | bar: May 1 to May 3; May 7 to May 10; May 13 to May 17; May 20 to May 24; May 27 to May 31; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
Service Setup / Installation S1 and Insight (On-Cloud AWS) (DEV, SIT, UAT) | CIMB, CRIF |  | Not start | Not start | bar: June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
Availability of the CIMB systems to be integrated from StrategyOne | CIMB |  | Not start | Not start | bar: Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
Training | bar: Aug 1 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Oct 31; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Jan 31; Feb 4; Feb 11; Feb 18; March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
Pre-requisite for training | bar: Jan 7; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
Trainees confirmed | CIMB | Risk , IT App | Not start | Not start | bar: Jan 7; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
Access to remote training (Dev env) - for trainees and trainer(s) : Firewall, create user | CIMB | Infra | Not start | Not start | bar: Jan 7; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
Strategy One Training (Policy Configuration) ( Business , Tech) | CIMB, BA | Risk , IT App | Not start | Not start | bar: Jan 7; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
Insight Standard Report Training ( Business , Tech) |  | Risk , IT App | bar: Aug 1 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Oct 31; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Jan 31; Feb 4; Feb 11; Feb 18; March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
System Training - Techinca (Tech, BU) | CIMB, BA | IT App, Risk | Not start | Not start | bar: Aug 1 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Oct 31; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Jan 31; Feb 4; Feb 11; Feb 18; March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
Configuration / Implementation/ Unit testing | bar: April 29 to May 3; May 7 to May 10; May 13 to May 17; May 20 to May 24; May 27 to May 31; June 3 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28; July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Sep 2 to Sep 6; Sep 9 to Sep 13; Sep 16 to Sep 20; Sep 23 to Sep 27; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Nov 2; Nov 5 to Nov 9; Nov 12 to Nov 16; Nov 19 to Nov 23; Nov 26 to Nov 30; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Feb 2; Feb 4 to Feb 9; Feb 11 to Feb 16; Feb 18 to Feb 22; Feb 25 to March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
- Credit Policy Configuration into Decision Engine | bar: July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Sep 2 to Sep 6; Sep 9 to Sep 13; Sep 16 to Sep 20; Sep 23 to Sep 27; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Nov 2; Nov 5 to Nov 9; Nov 12 to Nov 16; Nov 19 to Nov 23; Nov 26 to Nov 30; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Feb 2; Feb 4 to Feb 9; Feb 11 to Feb 16; Feb 18 to Feb 22; Feb 25 to March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
* Mortgage Loan [HL,MP,PL,HM] Need CIMB ?? | CRIF, CIMB |  | Not start | Not start | bar: July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Sep 2 to Sep 6; Sep 9 to Sep 13; Sep 16 to Sep 20; Sep 23 to Sep 27; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Nov 2; Nov 5 to Nov 9; Nov 12 to Nov 16; Nov 19 to Nov 23; Nov 26 to Nov 30; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Feb 2; Feb 4 to Feb 9; Feb 11 to Feb 16; Feb 18 to Feb 22; Feb 25 to March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
* Personal Loan [PC, EC] Need CIMB ?? | CRIF, CIMB |  | Not start | Not start | bar: Aug 1 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Sep 2 to Sep 6; Sep 9 to Sep 13; Sep 16 to Sep 20; Sep 23 to Sep 27; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Nov 2; Nov 5 to Nov 9; Nov 12 to Nov 16; Nov 19 to Nov 23; Nov 26 to Nov 30; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Feb 2; Feb 4 to Feb 9; Feb 11 to Feb 16; Feb 18 to Feb 22; Feb 25 to March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
* CIMB co-work configuration | CIMB, CRIF | Risk , IT App | Not start | Not start | bar: Aug 1 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Sep 2 to Sep 6; Sep 9 to Sep 13; Sep 16 to Sep 20; Sep 23 to Sep 27; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Nov 2; Nov 5 to Nov 9; Nov 12 to Nov 16; Nov 19 to Nov 23; Nov 26 to Nov 30; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Feb 2; Feb 4 to Feb 9; Feb 11 to Feb 16; Feb 18 to Feb 22; Feb 25 to March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
- RRCS Enhance for CRDE | CIMB | eBWox, IT App | Not start | Not start | bar: Aug 1 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Sep 2 to Sep 6; Sep 9 to Sep 13; Sep 16 to Sep 20; Sep 23 to Sep 27; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Nov 2; Nov 5 to Nov 9; Nov 12 to Nov 16; Nov 19 to Nov 23; Nov 26 to Nov 30; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Feb 2; Feb 4 to Feb 9; Feb 11 to Feb 16; Feb 18 to Feb 22; Feb 25 to March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
- Integration Configuration | bar: Aug 1 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Sep 2 to Sep 6; Sep 9 to Sep 13; Sep 16 to Sep 20; Sep 23 to Sep 27; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Nov 2; Nov 5 to Nov 9; Nov 12 to Nov 16; Nov 19 to Nov 23; Nov 26 to Nov 30; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Feb 2; Feb 4 to Feb 9; Feb 11 to Feb 16; Feb 18 to Feb 22; Feb 25 to March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
* LOS (XSLT) insert RRCS before line 50 ???? | CIMB,GT |  | Not start | Not start | bar: Aug 1 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Sep 2 to Sep 6; Sep 9 to Sep 13; Sep 16 to Sep 20; Sep 23 to Sep 27; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Nov 2; Nov 5 to Nov 9; Nov 12 to Nov 16; Nov 19 to Nov 23; Nov 26 to Nov 30; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Feb 2; Feb 4 to Feb 9; Feb 11 to Feb 16; Feb 18 to Feb 22; Feb 25 to March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
IQA - Check SIT API | CIMB | IQA | Not start | Not start | bar: Jan 7; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
System Integration Test | CIMB,GT | IT App | Not start | Not start | bar: Jan 7; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
Testing preparation - UAT |  | Risk | bar: July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Sep 2 to Sep 6; Sep 9 to Sep 13; Sep 16 to Sep 20; Sep 23 to Sep 27; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Nov 2; Nov 5 to Nov 9; Nov 12 to Nov 16; Nov 19 to Nov 23; Nov 26 to Nov 30; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Feb 2; Feb 4 to Feb 9; Feb 11 to Feb 16; Feb 18 to Feb 22; Feb 25 to March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
Testing preparation - Mortgage | bar: July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to July 31; Jan 7; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
Test strategy, UAT acceptance criteria | CIMB | Risk | Not start | Not start | bar: July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to July 31; Jan 7; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
Test plan, test cases and data preparation | CIMB | Risk | Not start | Not start | bar: July 1 to July 5; July 8 to July 12; July 15 to July 19; July 23 to July 26; July 30 to July 31; Jan 7; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
Testing preparation - PL | bar: Aug 1 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Oct 31; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Jan 31; Feb 4; Feb 11; Feb 18; March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
Test strategy, UAT acceptance criteria | CIMB | Risk | Not start | Not start | bar: Aug 1 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Oct 31; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Jan 31; Feb 4; Feb 11; Feb 18; March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
Test plan, test cases and data preparation | CIMB | Risk | Not start | Not start | bar: Aug 1 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Oct 31; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Jan 31; Feb 4; Feb 11; Feb 18; March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
Testing preparation - Insight | bar: Aug 1 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Sep 2 to Sep 6; Sep 9 to Sep 13; Sep 16 to Sep 20; Sep 23 to Sep 27; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Nov 2; Nov 5 to Nov 9; Nov 12 to Nov 16; Nov 19 to Nov 23; Nov 26 to Nov 30; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Feb 2; Feb 4 to Feb 9; Feb 11 to Feb 16; Feb 18 to Feb 22; Feb 25 to March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
Test strategy, UAT acceptance criteria | CIMB | Risk | Not start | Not start | bar: Aug 1 to Aug 2; Aug 5 to Aug 9; Aug 13 to Aug 16; Aug 19 to Aug 23; Aug 26 to Aug 30; Sep 2 to Sep 6; Sep 9 to Sep 13; Sep 16 to Sep 20; Sep 23 to Sep 27; Oct 30 to Oct 4; Oct 7 to Oct 11; Oct 14 to Oct 19; Oct 22 to Oct 26; Oct 29 to Nov 2; Nov 5 to Nov 9; Nov 12 to Nov 16; Nov 19 to Nov 23; Nov 26 to Nov 30; Dec 3 to Dec 7; Dec 10 to Dec 14; Dec 17 to Dec 21; Dec 24 to Dec 28; Dec 31 to Jan 4; Jan 7 to Jan 12; Jan 15 to Jan 19; Jan 22 to Jan 26; Jan 28 to Feb 2; Feb 4 to Feb 9; Feb 11 to Feb 16; Feb 18 to Feb 22; Feb 25 to March 1; March 4 to March 8; March 11 to March 15; March 18 to March 22; March 25 to March 30
Test plan, test cases and data preparation | CIMB | Risk | Not start | Not start | bar: Sep 2 to Sep 6; Sep 9 to Sep 13; Sep 16 to Sep 20; Sep 23 to Sep 27; Nov 1 to Nov 2; Nov 5 to Nov 9; Nov 12 to Nov 16; Nov 19 to Nov 23; Nov 26 to Nov 30; Jan 7; Jan 15; Jan 28; Feb 1 to Feb 2; Feb 4 to Feb 9; Feb 11 to Feb 16; Feb 18 to Feb 22; Feb 25 to Feb 28
CIMB UAT & Signoff | CIMB,GT | Risk | Not start | Not start | bar: Jan 7; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
CIMB Pen test (UAT ) | CIMB,GT | Security | Not start | Not start | bar: Jan 7; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
CIMB Performance test & Fine-tuning ( SIT or Prod ??) | CIMB,GT | K. Nong or User ? | Not start | Not start | bar: Jan 7; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
CIMB DR test | CIMB,GT | Thiti, Be, IT App, User | Not start | Not start | bar: Jan 7; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
CAB + Prod Prepar |  | Thiti, Be, IT App, User | bar: Jan 7; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
Technical Go Live | CIMB, BA, GT |  | Not start | Not start | bar: Jan 7; Jan 15; Jan 28; Feb 4; Feb 11; Feb 18
Note on AL22: Wirat Rajchakhom (Natt): Make conferrence if need
Note on AL87: Wirat Rajchakhom (Natt): Make conferrence if need
Note on AL185: Wirat Rajchakhom (Natt): Make conferrence if need

## Check list
No | Descriptions | DEV | SIT | UAT | PROD | Remark
1 | Implementation :
2 | 1. Design, Provisioning & Configuration for Elasticsearch, Logstash, Kibana and log collectors on Dev, PROD (Bank will deploy on SIT and UAT with Vendor assistance/support) and align with CIMB Thai Bank Standard and CRIF application design.
3 | 2. Provide automate deployment and configuration the systems by using IaC, scripts or tools for generate EC2 including AWS cloud platform setup, elastic installation/set up, load balancer and firewall using Terraform.
4 | 3. Provide/perform the standard security hardening on platforms (Elasticsearch, Logstash, Kibana) by using scripts or tools followed by Elasticsearch Security Guidelines.
5 | 4. Automate Start/Stop service and configure scheduling using Linux Crontab for scheduling & System for start/top.
6 | 5. Vulnerability fixing for Elasticsearch, Logstash, Kibana and Log collectors by using scripts or tools.
7 | 6. Implement data encryption at rest and in-transit on all components using Elasticsearch Security for data in-transit. For data at rest, we will implement in Amazon AWS Service.
8 | 7. Ensure data encryption at rest and in-transit on all components.
9 | 8. Provide Solution/Tools for backup and recovery and align with CIMB Thai Bank Standard. (RPO/RTO) using AWS storage back up.
10 | 9. Backup & Restoration both configuration and system deliver with IaC State file (infra level).
11 | 10. Configuring role base access control (RBAC) to authentication, authorization to secure access the Elastic Search cluster and data as Admin/developer/user roles that synced with Azure AD.
12 | Integration :
13 | 1. Provide Azure AD integration for authentication/authorization into Elasticsearch system followed CIMB practice.
14 | 2. Integrate to CRIF Insight using File Beat.
15 | 3. Integrate Kibana to Azure AD using standard set up.
16 | 4. Integrate Kibana to Elasticsearch using standard set up.
17 | 5. All secure setting and implementation i.e., key management, certification, SSL, etc. follow by Standard SSL/TLS/CA Cert
18 | 6. Internal communication can use Self-Sign Cert (Adjustable)
19 | 7. External communication can use Commercial Cert from CIMB
20 | 8. Platform monitoring: APM (or new integration) + Elasticsearch.
21 | Testing :
22 | 1. Support Operation test such as start/stop services, etc.
23 | 2. Support functional test (integrate with App)
24 | 3. Non-functional test
25 | Performance testing and tuning
26 | HA scenario testing (shutdown nodes)
27 | Backup and restore verification as AWS storage back up.
28 | 4. Support CIMB to testing, UAT and go-live process i.e., QA, performance test, HA, CAB, etc.
29 | 5. 2 months warrantee after Go-live.
30 | Operation and Support :
31 | 1. Elasticsearch, Logstash, Kibana and Log collector Patch, Vulnerability fixing, version & release recommendation and implementation.
32 | 2. Minor OS Patching and Upgrade version Support
33 | 3. Upgrade Minor Elastic, Logstash, Kibana and Log collector version Support and one time version Major upgrade Elastic.
34 | 4. Emergency patching and Vulnerability fixing as per agreed time frame.
35 | 5. Managed service 12 months after warrantee period
36 | 6. 24x7 for Platform Problem Resolution follow by agreed SLA.
37 | 7. 4 times (at least) for Preventive Maintenance for
38 | Health Checking and fine tuning
39 | Performance Tuning
40 | Maintenance scripts and provide automation scripts.
41 | Housekeeping
42 | Etc.
43 | 8. Improvement, recommendation, and Optimization including Performance, Capacity, Configuration and Costing
44 | 9. Provide and brief monthly operation report.
45 | 10. Onsite support will be 24 days/year (adjustable – next year number of day will be based on actual consumption)
46 | Delivery of Documentation and Training :
47 | 1. Implementation and deliver as a code.
48 | 2. Handover session for implementation
49 | 3. Knowledge Transfer and Documentation
50 | 4. Training (include LAB) both user and administration up to 25 persons each class.
51 | 5. Able to record all training class.
52 | 6. Documents
53 | 1. Design and architecture
54 | 2. UAT Sign-off
55 | 3. 7 docs follow by CIMB standard template.
56 | 4. Hardening baseline
57 | Licensing :
58 | 1. Elastic Search Platinum Edition Version 8.6.1 for support those environment
59 | 1. Production Environment 3 servers
60 | 2. SIT Environment 1 server
61 | 3. UAT Environment 1 server
62 | 4. DEV Environment 1 server

## Project Organization chart
k
No | Name |  | Project Role | Email: | Mobile: | Remark
1
2
3
4
5
6
7
8
9
10
11
12
13
14
ElasticSearch project
stakeholder
CS
CS2
Project Manager
Project Engineer
Project Sponsor
- Wirat - TH
- Clifton - SG
- XXX
Project Manager
Project Engineer - Contact point
Project Sponcor
- xxxx
- xx
- xxxx
- XXXX
-
- Name - TH
- Name - TH
- Name - TH

## CS Payment term
The possible payment when we track on project time line and plan :
- 40% after design phase and contract signed :
- 30% after UAT Sign Off :
- 30% after Go-Live, training and after warranty 2 months :

## Project plan - Week plan
Payment | CR | CUS | Task | PIC |  | Dep | Feb |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | Aug |  |  |  | Sept |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | March
[5 empty] | CIMB |  | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4
Phase 0 : System desing. | bar: Feb w4 to March w4
|  |  | Gathering Infor Design SIT, DEV,UAT,PROD Sign Off | A, B | bar: Feb w4 to March w2
|  |  | - Technical readiness brief - Elastic search technology | A, B | bar: March w1
|  |  | - VPN preparation and confirmation | A, B | bar: March w2 to March w4
|  |  | - Jump host access and collaboration confirm | A, B | bar: March w2 to March w4
|  |  | - Technical readiness content preparation | A, B | bar: March w3
|  |  | - Technical readiness - training day | A, B | bar: March w4 to April w1
|  |  | Develop standard Terraform to provision EKS | C | bar: March w2 to March w3
|  |  | Rolling Implementation by Environment | C | bar: March w2 to March w3
Phase 1 Dev: Project implementation | bar: Feb w2 to Feb w1
|  |  | Information Gathering and confirm AWS Design and ELK Design. Finalise design for DEV | A, B | bar: April w1 to April w2
|  |  | Final review and confirm AWS Design and ELK Design for DEV - Sign Off documents. | A, B | bar: April w2 to April w3
|  |  | Start Terraform and Ansible Setup and Testing (Need AWS access, VPN to Jumpbox and setup Jumpbox), Provision Dev,ELK | A, B | bar: April w3 to May w3
|  |  | Integration - CRIF Insight , Azure AD (INRA ) | A, B | bar: May w2 to May w3
|  |  | Kubernetes | C | bar: April w3 to June w2
|  |  | Authen & Firewall | C | bar: May w2 to June w2
Phase 2 SIT: Project implementation | bar: Feb w2 to Feb w1
|  |  | Information Gathering and confirm AWS Design and ELK Design for SIT (and others) | C | bar: May w2 to May w3
|  |  | Final review and confirm AWS Design and ELK Design for SIT - Sign Off documents. | C | bar: May w3 to May w4
|  |  | Provision the UAT Environment, ELK | C | bar: May w4 to June w2
|  |  | Integration - CRIF Insight , Azure AD | C | bar: June w3
|  |  | Kubernetes , CI/ CD | C | bar: May w4 to July w3
|  |  | VA scan , harden (After App DONE) | C
|  |  | Authen & Firewall | C | bar: June w3 to July w3
Phase 3 UAT: Project implementation | bar: Feb w2 to Feb w1
Information Gathering and confirm AWS Design and ELK Design. Finalise design for UAT env | bar: July w2 to July w3
Final review and confirm AWS Design and ELK Design for UAT - Sign Off documents. | bar: July w3 to July w4
|  |  | Start Terraform and Ansible Setup and Testing, Provision the DEV Environment & ELK, UAT | A, B | bar: Aug w1 to Aug w4
|  |  | Integration - CRIF Insight , Azure AD | A, B | bar: Sept w1
|  |  | Kubernetes , CI/ CD | A, B | bar: Aug w1 to Sept w4
|  |  | APM (After Imp CRIF Insight) | A, B | bar: Oct w1 to Oct w2
|  |  | Prisma cloud | A, B | bar: Oct w1 to Oct w2
|  |  | Authen & Firewall | A, B | bar: Aug w4 to Sept w4
|  |  | Draft 7 Docs (Discuss only one or separate ??? ) | A, B | bar: Aug w1 to Oct w2
Phase 4 PROD: Project implementation | bar: Feb w2 to Jan w3
Information Gathering and confirm AWS Design and ELK Design. Finalise design for PROD | bar: Sept w1 to Sept w3
40% |  |  | Final review and confirm AWS Design and ELK Design for PROD - Sign Off documents. | bar: Sept w3 to Oct w1
|  |  | AWS IaC coding and development , Deploy AWS EC2 & ELK for PROD | A, B | bar: Oct w4 to Nov w3
| CR |  | Integration - CRIF Insight , Azure AD (Microsoft AD) | A, B | bar: Nov w3
A, B | bar: Nov w4
|  |  | Kubernetes , CI/ CD | A, B | bar: Nov w3 to Jan w1
|  |  | APM (After Imp CRIF Insight) | A, B | bar: Jan w2 to Jan w3
|  |  | Prisma cloud | A, B | bar: Jan w2 to Jan w3
|  |  | Authen & Firewall | A, B | bar: Nov w4 to Dec w4
|  |  | Review and Sign Off 7 Docs (Discuss only one or separate ??? ) | A, B | bar: Nov w4 to Dec w4
Application Implementation | bar: Feb w2 to Feb w1
Soft Freeze | bar: April w1 to Dec w2
Hard Freeze | bar: Dec w3 to Feb w1
Analysis | bar: April w1 to Aug w2
|  |  | - Preliminary Analysis + As-is Credit Process Review (Mortgage , PL) | A, B | Risk , IT App | bar: April w1 to May w1
|  |  | - Detailed Analysis - To-be Credit Process - Mortgage | A, B | Risk , IT App | bar: May w1 to June w1
|  |  | - Detailed Analysis - To-be Credit Process - PL | A, B | Risk , IT App | bar: June w1 to July w1
|  | S | - Insight functionality review for CIMB | A, B | Risk , IT App | bar: April w3 to May w1
|  | S | - Insight functionality confirmation | A, B | Risk , IT App | bar: May w1 to May w3
|  |  | - Preliminary Analysis + technical architecture | A, B | IT App , Thiti, Be | bar: April w2 to May w3
|  |  | - Detailed Analysis - To-be Architecture | A, B | IT App , Thiti, Be | bar: May w3 to June w3
Documentation
|  |  | FSD Prep - Mortage | A, B | Risk , IT App | bar: June w1 to June w3
|  |  | FSD - Mortgage - sign off | A, B | Risk , IT App | bar: June w3 to June w4
|  |  | FSD Prep - PL | A, B | Risk , IT App | bar: July w1 to July w3
|  |  | FSD - PL sign off | A, B | Risk , IT App | bar: July w3 to July w4
FSD Prep - Insight + Non Functional | bar: July w4 to Aug w1
FSD - Insight + Non Functional sign off | bar: Aug w1 to Aug w2
|  |  | TSD Prep (Crete and Review ???) | A, B | IT App | bar: June w3 to July w1
|  |  | TSD - sign off | A, B | IT App | bar: July w1 to July w2
Technical | bar: April w1 to June w2
|  |  | System setup complete based on system requirement | A, B | bar: April w1 to May w1
|  |  | AWS infrastructure is ready based | A, B | bar: May w1
|  |  | Service Setup / Installation S1 and Insight (On-Cloud AWS) (DEV, SIT, UAT) | A, B | bar: May w2 to June w2
|  | LOS | Availability of the CIMB systems to be integrated from StrategyOne | A, B | bar: June w4
Training | bar: July w3 to Aug w2
Pre-requisite for training | bar: July w3 to July w4
|  |  | Trainees confirmed | A, B | Risk , IT App | bar: July w3 to July w4
|  |  | Access to remote training (Dev env) - for trainees and trainer(s) : Firewall, create user | A, B | Infra | bar: July w3 to July w4
|  |  | Strategy One Training (Policy Configuration) ( Business , Tech) | A, B | Risk , IT App | bar: July w3 to July w4
|  |  | Insight Standard Report Training ( Business , Tech) |  | Risk , IT App | bar: July w4 to Aug w1
|  |  | System Training - Techinca (Tech, BU) | A, B | IT App, Risk | bar: July w4 to Aug w2
Configuration / Implementation/ Unit testing | bar: April w2 to Jan w2
- Credit Policy Configuration into Decision Engine | bar: June w4 to Oct w4
|  |  | * Mortgage Loan [HL,MP,PL,HM] | A, B | bar: June w4 to Sept w4
|  |  | * Personal Loan [PC, EC] | A, B | bar: Aug w1 to Oct w4
|  |  | * CS co-work configuration | A, B | Risk , IT App | bar: Aug w1 to Oct w2
|  | CS Task | - RRCS Enhance for CRDE | A, B | eBWox, IT App | bar: July w2 to Sept w2
- Integration Configuration | bar: Aug w1 to Sept w3
|  |  | * LOS (XSLT) insert CS before line 50 ???? | A, B | bar: Aug w1 to Sept w4
|  | CS Task | IQA - Check SIT API | A, B | IQA | bar: Sept w3 to Oct w1
|  |  | System Integration Test | A, B | IT App | bar: Oct w4 to Nov w4
|  |  | Testing preparation - UAT |  | Risk | bar: June w4 to Sept w3
|  | BU-User | Testing preparation - Mortgage | bar: June w4 to July w3
|  |  | Test strategy, UAT acceptance criteria | A, B | Risk | bar: June w4 to July w1
|  |  | Test plan, test cases and data preparation | A, B | Risk | bar: July w1 to July w3
Testing preparation - PL | bar: July w4 to Aug w3
|  |  | Test strategy, UAT acceptance criteria | A, B | Risk | bar: July w4 to Aug w1
|  |  | Test plan, test cases and data preparation | A, B | Risk | bar: Aug w1 to Aug w3
Testing preparation - Insight | bar: Aug w1 to Sept w1
|  |  | Test strategy, UAT acceptance criteria | A, B | Risk | bar: Aug w1 to Sept w3
|  |  | Test plan, test cases and data preparation | A, B | Risk | bar: Aug w3 to Sept w1
30% |  |  | CS UAT & Signoff | A, B | Risk | bar: Nov w4 to Jan w2
|  |  | CS Pen test (UAT ) | A, B | Security | bar: Jan w3 to Jan w4
|  |  | CS Performance test & Fine-tuning ( SIT or Prod ??) | A, B | K. Nong or User ? | bar: Dec w2 to Jan w1
|  |  | CS DR test | A, B | Thiti, Be, IT App, User | bar: Jan w4 to Feb w2
Thiti, Be, IT App, User | bar: Feb w1 to Feb w4
30% |  |  | Technical Go Live | A, B | bar: March w1
Note on AM39: Wirat Rajchakhom (Natt): Possible payment : 40%
Note on AZ100: Wirat Rajchakhom (Natt): Possible payment : 30%
Note on BG105: Wirat Rajchakhom (Natt): Passible payment : 30%